## Slide 1
NZQA
Performance Update
January – March 2026

## Slide 2: Introduction
Executive summary
This report summarises NZQA’s performance in January – March 2026. It is designed to give readers a high-level picture of NZQA's performance at the time of writing so some items fall outside of this date range.
Looking forward NZQA will:
For the year-to-date, NZQA:
Continued work with the Ministry preparing for new senior secondary qualifications.
Continued to address recommendations from independent reviews of the in-house NZQA Automated Text Scoring (ATS) model.
Successfully released NCEA results on 14 January 2026, where ~92,000 students logged onto the student portal to view their results.
Began implementing our tertiary integrated quality assurance framework (the iQAF) now that new Rules are in force.
Completed planning for the review of Te Hono o Te Kahurangi, and started engaging with Māori providers to gather feedback and recommendations.
Developed revised outyear financial forecasts based on assumptions for Budget 26. Subject to Budget 26 decisions, NZQA is now well positioned to remain financially robust.
Implemented a 90-day planning approach to ensure change and delivery responsibilities are well managed.
NZQA is one of the agencies that manage and regulate the education system in New Zealand. We work with other education agencies to make sure education is high-quality and running well in New Zealand.
This is achieved through its stewardship of the New Zealand Qualifications and Credentials Framework, managing the qualifications system, regulating and quality assuring non-university tertiary education, delivering credible senior secondary school external assessment, quality assuring secondary school internal assessment, and administering the Education Code of Practice 2021.
Look to shortlist standards that can be marked by AI in a live environment in 2027, prioritising standards that are expected to endure after the proposed NCEA changes.
Continue our work with the Ministry to prepare to implement decisions around the replacement of NCEA.
Deliver information sessions to support sector readiness for the TEO self review process within the iQAF, and engage with agencies and sector representatives on proposed TEO quality descriptors.
Finalise Budget 26 Bids.

## Slide 3: Strategic priorities
NZQA Performance Update
NZQA’s strategic priorities are:
Perform core functions well, supported by strong corporate infrastructure.
Improve stakeholder trust and confidence in current and future qualifications and credentials.
Utilise right touch, right size regulation that balances the needs of all stakeholders.
Leverage digital solutions to increase business efficiency and quality.
This section discusses work underway to achieve selected priorities.
1
2
3
4

## Slide 4: Progress on selected strategic priorities
Looking forward, NZQA will:
Finalise Budget 26 bids. These bids consider all costs including staffing needs.
Continue to track NZQA’s progress against the FPP.
Continue to focus on efficiencies and cost management
Over the last three months, we have:
Worked closely with the Treasury and Ministry to progress a suite of Budget 26 bids. At the time of writing all bids are expected to be fully or partially funded.
Replaced the Financial Stabilisation Plan with the FPP, and developed our 2026/27 budget. If NZQA’s budget bids are successful, NZQA is well positioned to remain financially robust while delivering its core responsibilities into the future.
Strategic Priorities
Over the last three months, we have:
Progressed our people leader development programme to support effective change management, and prompted all staff to plan the skills and knowledge needed for future capability.
Continued to focus on change management maturity and coordination, and resourcing and support for key projects.
Implemented a 90-day planning process to ensure NZQA is well placed to deliver on its BAU and change responsibilities.
Looking forward, NZQA will:
Continue to work with the Ministry to prepare to implement decisions around the replacement of NCEA.
Continue budgeting and business planning for FY 2026/27, driving effective, efficient delivery of core services.
Continue our people leader development programme, and encourage staff to develop skills and knowledge needed for future capability.
Financial Position and Projection
NZQA developed a medium term Financial Position and Projection (FPP) to reflect its progress in achieving financial sustainability.
NZQA’s Change Agenda
We continue to balance core service delivery with large pieces of change work.

## Slide 5: Secondary Assessment
NZQA administers, quality assures and reports on senior secondary credentials (including NCEA, New Zealand Scholarship and University Entrance). Responsibilities include:
Quality assuring senior secondary schools’ assessment systems through Consent to Assess and Managing National Assessment Reviews.
Delivering external NCEA and New Zealand Scholarship assessments.
Moderating internally assessed achievement standards and providing assessor support.
This section discusses work underway to achieve selected priorities.
1
2
3

## Slide 6: Strategic priorities
AI developments for marking assessments
This quarter we continued to address the recommendations from the independent reviews of the in-house NZQA Automated Text Scoring (ATS) model. This involved developing Machine Learning Operations (MLOps) work to ensure NZQA’s AI marking model could be reliably used and maintained in live environment, and completing the technical documentation that support development and operational use.
NZQA has completed ‘Proof of Concepts’ (PoCs) for AI marking of three NCEA standards. These PoCs achieved promising results. A new PoC was started to explore how AI might be used to moderate secondary school marked internal assessments.
Looking forward
We will address the final recommendations from the ATS reviews. For AI marking of NCEA standards, we will now look to shortlist those that can be marked by AI in a live environment in 2027, prioritising curriculum areas that are expected to endure after the proposed NCEA changes.
Digital Developments – Authenticity of Assessments
The Authenticity project aims to safeguard the integrity of NCEA assessments by addressing growing digital risks to assessment authenticity. In this quarter we laid the groundwork for the refresh of the Digital Authenticity Strategy. We also began small-scale trials of screen recording for invigilation and plagiarism detection tools to assess feasibility, accuracy, and user impact. A PoC is underway with two vendors to gather insights on two potential solutions.
Looking forward
We will refresh the Digital Authenticity Strategy and continue the PoC to explore screen recording.
Minister’s proposal to replace NCEA
In March Cabinet confirmed the replacement of NCEA and the main structural components of the new qualifications system. In the months leading up to this, we continued to support the Ministry of Education and to work with the NCEA Professional Advisory Group and the National Qualifications Technical Advisory Group on the proposal to replace NCEA. This included contributing to a Cabinet paper and ensuring alignment between plans for the assessment criteria authentically with work on the new curriculum subjects. We also progressed our internal planning to support implementation of the new qualification and assessment system.
Looking forward
We will continue work with the Ministry of Education, to support the next phase of technical decisions. We will also start work with Universities New Zealand to review University Entrance (UE) in line with the new qualifications.
NZQA Performance Update
Secondary Assessment

## Slide 7: Operational overview
NZQA Performance Update
Secondary Assessment
Strengthening NCEA Quality Assurance and support for schools and kura
We continued our risk-based approach to strengthen school and kura NCEA quality assurance, including:
delivering a number of seminars and webinars focused on improving consistency in how assessment requirements are applied (this includes standard conditions, evidence requirements, moderation expectations, practices and processes).
working with schools and kura to develop a new Special Assessment Conditions (SAC) auditing process. This will support confidence that assessment supports are being applied appropriately, equitably and consistently.
identifying schools and kura that require confirmatory moderation by looking at indicators of non-compliance.
undertaking seminars and webinars to build assessment capability, reinforce national expectations, and support consistent implementation of NCEA.
engaging with kura that are participating in a project to strengthen the capability of assessors to understand their needs and perspectives.
Looking forward
In the next quarter, we will:
carry out quality assurance activities to determine whether schools and kura continue to meet the requirements for Consent to Assess.
undertake quality assurance check-ins for schools and kura that are not scheduled for a Managing National Assessment review this year.
undertake confirmatory moderation on selected assessments to target additional assurance activities.
offer webinars for just in time learning for schools and kura.
gather feedback on the resource package to improve assessor capability, and support the rollout of the finished product with kura.
These activities support our focus on aligning regulatory effort with system risk, sustaining sector capability, and maintaining confidence in the credibility and consistency of assessment outcomes.
Results release – NCEA and Scholarship
We successfully released NCEA results on 14 January 2026, where ~92,000 students logged onto the student portal to view their results, and NZ Scholarship results on 10 February 2026.

## Slide 8: Qualifications and TEO Quality Assurance
NZQA is responsible for:
Maintaining the New Zealand Qualifications and
Credentials Framework (NZQCF).
Administering the Education (Pastoral Care of Tertiary and International Learners) Code of Practice 2021.
Setting Rules for and monitoring tertiary education
organisations (TEOs).
Meeting New Zealand’s education-related international obligations.
Quality assurance of tertiary education organisations (excluding universities).
Recognising international qualifications and supporting the international recognition of New Zealand qualifications.
This section discusses work underway to achieve selected priorities.
1
4
2
5
3
6

## Slide 9: Strategic priorities
NZQA Performance Update
Integrated Quality Assurance Framework (iQAF)
With new Rules in force from 19 January 2026, our work to implement the iQAF continues to progress well. Several milestones were reached in the quarter.
The new annual self review process for Tertiary Education Organisations (TEOs) is on track to be launched in July, supported by strong communications to TEOs and Industry Skills Boards (ISBs).
The development of overall TEO quality descriptors is well underway, with public consultation planned for June.
We are working with the Tertiary Education Commission and Immigration New Zealand to set up information sharing agreements that support consistent cross agency decision making and reduce the administration burden on providers. Specifically, with the Tertiary Education Commission, we are working closely together to identify and reduce duplicative reporting requirements on TEOs.
Our internal organisational structure for the Quality Assurance Division is in place. This included establishing new functions. Some recruitment is still underway.
Looking forward
In the next quarter we will deliver information sessions to support sector readiness for the TEO self review process, and engage with agencies and sector representatives on proposed TEO quality descriptors.
A risk-informed approach to our quality assurance activities is one of the three enablers of the iQAF. Our updated risk framework will be published in the next quarter and outlines how we will systematically and proactively identify risk (at both TEO and system level), verify compliance, and manage non-compliance.
Implementing a simpler, fairer fee system
We have implemented the first stage of the simpler, fairer fee system for TEOs by extending the credit reporting fee to include qualification completions for all TEOs other than universities. This included a reduction in the credit fee from $1.37 to $1.10 (GST exclusive) effective 1 January 2026.
We introduced a new credit fee for qualification completions completed after 19 January 2026, and this is progressing well. We have established a TEO feedback group to contribute to the design of the billing methodology and the communications to support implementation.
A review of fees for NZQA’s Qualifications Recognition Services (QRS) has been completed to ensure consistency of QRS fees are based on NZQA’s cost recovery guidance. Recommendations have been considered by the NZQA Board.
Looking forward
In the next quarter we will start billing TEOs for the credit value of completed qualifications, and publicise any changes to the QRS fee schedule. If changes go ahead, we expect they will take effect from 1 January 2027.
Qualifications and TEO Quality Assurance

## Slide 10
NZQA Performance Update
Qualifications and TEO Quality Assurance
Operational overview
Approvals & applications
  We continue to support the Vocational Education & Training (VET) reforms and establishment of the ISBs by meeting ISB teams and staff and assisting with the transition of work in progress (WIP). The polytechnics have their own profile records correctly reflecting their approvals and accreditations, and this has been confirmed with each organisation. We are also supporting the transition of former work-based learning divisions from ISBs to their new entities including work on two PTE registration applications for new entities; and is also supporting associated changes to work-based learning and subcontracting related rules.
  We closed over 300 applications in the quarter, including >50 applications for ISBs (WIP handed over from WDCs to ISBs), 59 new skill standards, >80 applications for the polytechnics, and two PTE registration applications (both were former divisions of NZIST).
Statutory actions and monitoring
NZQA monitors tertiary education providers (other than universities) to help ensure that providers are delivering what they promise students and are complying with the rules that we set. In this quarter we:
focused our monitoring on areas that are of higher concern, such as construction, teaching and early childhood qualifications, and maritime micro-credentials and qualifications, and
followed up with providers where earlier monitoring had found problems.
More providers were compliant the last quarter than at the end of last calendar year.
Where we find evidence of ongoing non-compliance with the rules, or where learners have been disadvantaged by a TEO’s practice, NZQA takes statutory action. In this quarter we assessed 56 concerns, opened eight new investigations, and closed 19. Some of the cases closed this quarter came from earlier monitoring work where providers had shown they had taken action. 28 investigations are still under way, and most will move forward next quarter.
Te Hono o Te Kahurangi review
Te Hono o Te Kahurangi is a whare ako framework and methodology that allows providers to engage with NZQA using Māori approaches and values. In this quarter we completed planning for the review of Te Hono o Te Kahurangi, and started engaging with providers to gather feedback and recommendations.
Looking forward
In the next quarter, we will continue our review work, looking at whether changes to the framework are needed alongside the changes to our quality assurance regulatory approach brought in as part of iQAF.

## Slide 11: Operational overview
Overseas qualifications recognition applications
NZQA evaluates applications from individuals seeking to have their overseas tertiary and vocational qualifications recognised for immigration, employment or further study purposes.
The application pipeline was increasing for much of 2025. The current pipeline contains ~4,600 applications, up slightly from the last quarter, and the wait time remains stable at 10 weeks.
We are working through options to reduce the pipeline, while also considering how to improve the application management system used for applications, through automated filtering of incomplete applications or through the use of AI. We are also trialling changes to people, process and technology that balance risk and integrity of decision-making, while also recognising the legitimate concerns of our customers and stakeholders about timeliness.
Looking forward
In the next quarter, we will continue our work to reduce the application pipeline and improve our application management system.
NZQA’s work in international education
Advancing the international reputation of New Zealand qualifications
NZQA continues to meet New Zealand’s obligations under UNESCO qualifications recognition conventions and to strengthen the international reputation of New Zealand’s qualifications. Highlights from the quarter include:
refining our approach to the recognition of refugee qualifications in line with the UNESCO Global Convention, particularly for individuals without documentation, in alignment with the Cabinet‑directed review of the New Zealand Refugee Resettlement Strategy.
contributing to a number of international forums, where we shared New Zealand’s experience as a global front‑runner in formalising micro‑credentials and qualifications recognition practices.
publishing the latest update to the Tertiary Education Qualification Statement (TEQS), New Zealand’s equivalent of a Diploma Supplement.
Progressing the Pacific Qualifications Recognition (PQR) project
NZQA is contracted by the Ministry of Foreign Affairs and Trade to strengthen the national and regional qualifications systems for the nine Pacific countries that are party to the PACER Plus trade agreement.
This quarter, participating countries have finalised national plans to strengthen their qualifications systems. We are working with the Pacific Community, bodies of international representatives and each country to implement these plans.
Looking forward
In the next quarter we will support actions to grow international education under the International Education Going for Growth Plan and Priority six of the Tertiary Education Strategy. We will also continue to support the implementation of the plans developed under the PQR project.
NZQA Performance Update
Qualifications and TEO Quality Assurance

## Slide 12: Financial performance for the quarter
NZQA completed a revised F2 Forecast for the full year 2025/26 in Quarter 3. This was approved by the Board in April 2026 and therefore is not reflected in the figures reported in this paper. Our revised F2 forecast shows NZQA is on track for a modest surplus of $0.25m.
Accordingly, comparative forecast balances are based on the first forecast (F1) approved in December 2025, with key movements previously explained in the Quarter 2 report.
The year-to-date (YTD) quarter 3 result is a net surplus of $2.7m. Business-as-usual (BAU) operations contributed a net surplus of $0.4m, with the overall result largely driven by lower-than-expected project expenditure. A portion of this project underspend is timing-related, and is expected to be incurred later in the year or deferred into the following financial year. The approved F2 Forecast will reflect the updated timing and status of project expenditure.

## Slide 13: Financial performance
NZQA Performance Update
Financial performance
 | Year to Date (31 March 2026) |  |  |  |  | Full Year |  | 
 | Actual | Forecast | Variance* | Budget |  | Forecast | Budget | Last Year
REVENUE |  |  |  |  |  |  |  | 
Crown Revenue | 64,104 | 64,101 | - | 66,756 |  | 81,512 | 84,812 | 79,575
Total Fee & Charges | 22,769 | 22,925 | (156) | 22,465 |  | 29,821 | 28,895 | 29,469
Other Income | 2,041 | 1,918 | 123 | 1,357 |  | 2,396 | 1,695 | 2,233
Total Revenue | 88,914 | 88,947 | (32) | 90,578 |  | 113,730 | 115,402 | 111,277
Personnel & Board | 44,691 | 44,378 | (313) | 42,816 |  | 59,007 | 57,356 | 58,040
Examination Workforce | 10,557 | 9,762 | (795) | 9,636 |  | 9,762 | 9,636 | 9,244
Specialist Workforce | 9,981 | 9,921 | (60) | 10,633 |  | 12,477 | 12,365 | 11,630
Professional Services | 3,302 | 3,983 | 681 | 4,650 |  | 5,390 | 6,021 | 6,012
Publication, print & distribution | 3,287 | 3,484 | 197 | 3,350 |  | 3,800 | 3,663 | 3,588
Travel & Accommodation | 941 | 1,054 | 113 | 1,119 |  | 1,397 | 1,425 | 1,013
IT costs | 7,857 | 8,162 | 305 | 8,579 |  | 10,774 | 11,559 | 10,063
Other operating | 7,267 | 7,317 | 51 | 6,953 |  | 9,102 | 9,434 | 9,136
Depreciation | 593 | 629 | 36 | 769 |  | 1,083 | 1,315 | 1,413
Total Expenses | 88,477 | 88,691 | 214 | 88,505 |  | 112,793 | 112,774 | 110,139
Net Operational Surplus | 437 | 256 | 181 | 2,072 |  | 937 | 2,628 | 1,138
Projects |  |  |  |  |  |  |  | 
Crown Funding | 8,962 | 8,962 | - | 6,412 |  | 11,600 | 8,300 | 10,000
Expenses | 6,662 | 9,557 | 2,895 | 8,750 |  | 13,063 | 10,826 | 8,037
Net investment in projects | 2,300 | (595) | 2,895 | (2,338) |  | (1,463) | (2,526) | 1,963
Net surplus/(deficit) | 2,737 | (339) | 3,076 | (265) |  | (526) | 102 | 3,101
Total Revenue is in line with forecast expectations.
Total expenses is also substantially in line with forecast expectations. Examination workforce costs are higher than forecast due to high than expected assessment volumes and increased uptake of Special Assessment Conditions (SAC). This is offset by lower than forecast Contractors & Consultants and IT related expenditure driven by NZQA’s targeted cost reduction efforts.
Net investment in projects is favourable against forecast due to timing differences in project expenditure YTD.
Net surplus is ahead of forecast primarily due to the net investment in projects noted above.
All figures are in $000's
*Variance Actual to Forecast

## Slide 14: Financial performance (cont.)
Insights – Balance Sheet
The Balance Sheet as at 31 March 2026.
NZQA Performance Update
Current Assets of $41.8m as at the end of quarter 3 are higher than last financial year-end 2024/55, due to the receipt of Crown revenue in advance. The funds in advance are held in a series of short term deposit investments to maximise interest earnings, and maturities are managed to be available when required.
Current Liabilities of $23.5m are also high than previous years due to the recognition of Crown revenue in advance as a liability.
Net Equity of $18.2m is higher than budgeted, due to our positive results YTD. Net equity has continue to be maintained above the target level as specified by NZQA’s Financial Reserves Policy.
 | 31 March 2026 |  | 30 June 2026 |  | 30 June 2026 |  | 30 June 2025
 | Actual |  | Forecast |  | Budget |  | Last year
Current Assets | 37,896 |  | 23,993 |  | 21,151 |  | 27,404
Non-Current Assets | 3,938 |  | 4,467 |  | 6,913 |  | 2,726
Total Assets | 41,834 |  | 28,460 |  | 28,064 |  | 30,130
Current Liabilities | 23,023 |  | 12,912 |  | 13,144 |  | 14,056
Non-Current Liabilities | 536 |  | 537 |  | 550 |  | 536
Total Liabilities | 23,560 |  | 13,449 |  | 13,694 |  | 14,593
Net Assets / Equity | 18,274 |  | 15,011 |  | 14,370 |  | 15,537
Financial performance
Financial Performance and Total Equity – projection
Chart: $000
| 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Revenue | 91051 | 101644 | 103881 | 107132 | 106303 | 114536 | 121277 | 125330
Expenses | 89199 | 97798 | 97354 | 101226 | 122358 | 125006 | 118176 | 125856
Net surplus/(deficit) | 1852 | 3846 | 6527 | 5906 | -16055 | -10470 | 3101 | -526
Total Equity | 16045 | 26308 | 32835 | 38961 | 22906 | 8092 | 15537 | 15011

## Slide 15: Non-financial performance for the quarter
Seven of the 15 accountability measures are reported at the end of Quarter 3. Of these, all seven met or exceeded target.

## Slide 16: Non-financial performance
Unaltered marker judgements post reconsideration |  |  |  |  | 
The percentage of all National Certificate of Educational Achievement (NCEA) marker judgements unaltered following Review or Reconsideration of External Assessment Results processes. |  |  |  | Target | YTD
 |  |  |  | 99.7% | 99.7%
Past results |  |  |  |  | 
2022/23 | 2023/24 | 2024/25 |  |  | 
99.7% | 99.7% | 99.7% |  |  | 
Supporting aromatawai and assessment practices |  |  |  | 
The percentage of kura and schools that agree or strongly agree that NZQA’s quality assurance practices support them to improve their aromatawai and assessment practices. |  |  | Target | YTD
 |  |  | 75% | 82%
Past results |  |  |  | 
2023/24 (established) | 2024/25 |  |  | 
96% | 76.9% |  |  | 
NZQA Performance Update
All of the measures reported in quarter 3 met target. This includes two measures that are reported in every quarter, and five assessment related measures that are only measured after quarter 3. The results for three of these are provided below.
Results
NZQA’s 2025/26 Statement of Performance Expectations includes 15 performance measures, of which nine are appropriations measures. Two measures are reported every quarter. Five are reported only in Quarter 3.
Non-financial performance
Digital participation in examinations |  |  |  | 
The percentage of Year 11s who participated in the NCEA co-requisite assessments (cumulative, as at end of the academic year). |  |  | Target | YTD
 |  |  | 75% | 95%
Past results |  |  |  | 
2024/25 (established) |  |  |  | 
91.5% |  |  |  |